## Dashboard
PayNow Integration Estimation
Presale strategy for SCSKAP: low-budget-friendly phased approach with controlled scope and visible risk items.
Recommended Strategy |  |  |  |  | Option | Min MD | Max MD
Start with Phase 0 fixed-scope discovery, then quote Phase 1 Lean MVP for Counter Sales only. Keep Field Power Integration as Phase 2. This protects margin because UOB API access, bank callback rules, SAP output technology, and SAP FI/AR clearing are not yet confirmed. |  |  |  |  | Phase 0 | 5 | 8
[5 empty] | Lean P1 | 45 | 75
[5 empty] | Standard P1 | 70 | 110
[5 empty] | Phase 2 | 30 | 50
Option | Min MD | Max MD | Avg MD | Positioning
Phase 0 Discovery | 5 | 8 | 6.5 | Recommended first step
Lean Phase 1 MVP | 45 | 75 | 60 | Best fit for low budget
Standard Phase 1 | 70 | 110 | 90 | If customer wants reliability
Phase 2 Field Power | 30 | 50 | 40 | Separate later phase
Key Commercial Guardrails
1 | Do not quote full scope until Phase 0 confirms UOB API, SAP output, and SAP update mechanism.
2 | Use fixed price only for Phase 0 and tightly scoped Phase 1; exclude bank onboarding delays and major SAP redesign.
3 | Base offer should be Lean Phase 1. Price exception handling, auto-clearing, dashboards, refunds, and Field Power separately.
4 | Customer budget is low, but project should be framed as ERP payment integration, not only QR generation.

## Phase Estimates
Phase Estimates
Summary options generated from the Work Breakdown sheet.
Phase | Scope | Min MD | Max MD | Avg MD | Best Use | Commercial Model | Elapsed Time | Recommendation
P0 | Phase 0 Discovery and Design | 5 | 8 | 6.5 | Recommended first | Fixed price | 1-2 weeks | Fixed-scope technical discovery before build commitment
P1L | Lean Phase 1 MVP | 45 | 75 | 60 | Best fit for low budget | Fixed scope or capped T&M | 6-8 weeks | Counter Sales MVP with core QR/payment/callback/SAP confirmation
P1S | Standard Phase 1 | 70 | 110 | 90 | Use if reliability matters more than lowest cost | Scoped fixed price | 8-12 weeks | Lean MVP plus stronger validation, exception handling, and reconciliation
P2 | Phase 2 Field Power Integration | 30 | 50 | 40 | Estimate after Phase 1 | Separate phase | TBD after Phase 1 | Extend payment flow to Field Power/mobile/field sales
Suggested Proposal Position
1 | Offer Phase 0 as a paid fixed-scope discovery. This gives customer a low starting cost and gives Rikkeisoft enough facts to protect margin.
2 | Use Lean Phase 1 as the base implementation. It covers business value without overbuilding exception handling or Field Power.
3 | Quote Standard Phase 1 only if customer explicitly needs production-grade reconciliation and lower manual operations.
4 | Keep Phase 2 as a separate post-MVP extension.

## Work Breakdown
Work Breakdown
Editable man-day estimate by phase/workstream. Phase Estimates uses SUMIF formulas from this sheet.
Phase | Work Item | Min MD | Max MD | Avg MD | Criticality | Notes
P0 | Requirement workshop and scope confirmation | 1 | 2 | 1.5 | Must-have | Confirm Counter Sales and Phase 2 boundary
P0 | SAP invoice/output review | 1 | 2 | 1.5 | Must-have | Identify ECC/S4/B1 and form technology
P0 | UOB API / PayNow QR feasibility review | 1 | 2 | 1.5 | Must-have | Confirm sandbox, OAuth2, QR data, webhook
P0 | Solution architecture and data flow | 1 | 1 | 1 | Must-have | Architecture, integration options, risk list
P0 | Final MVP estimation and delivery plan | 1 | 1 | 1 | Must-have | Basis for Phase 1 quote
P1L | Project setup and detailed design | 2 | 4 | 3 | Must-have | Keep design lean and implementation-ready
P1L | SAP invoice data mapping | 2 | 4 | 3 | Must-have | Invoice no, amount, customer, reference
P1L | SAP invoice output enhancement / QR placement | 6 | 10 | 8 | Must-have | Likely ABAP/form enhancement effort
P1L | Integration service setup | 3 | 5 | 4 | Must-have | Lightweight middleware/API service
P1L | UOB OAuth2 / API integration | 4 | 7 | 5.5 | Must-have | Token, certificates, bank API security
P1L | PayNow QR data generation/handling | 3 | 6 | 4.5 | Must-have | Dynamic amount and payment reference
P1L | Bank notification callback endpoint | 4 | 6 | 5 | Must-have | Receive UOB/SG Bank payment notification
P1L | Basic payment matching by invoice reference | 4 | 6 | 5 | Must-have | Match payment reference to SAP invoice
P1L | SAP payment confirmation/status update | 5 | 8 | 6.5 | Must-have | Confirm paid status or posting interface
P1L | Basic logs and error handling | 3 | 5 | 4 | Must-have | Audit API calls, callbacks, errors
P1L | SIT/UAT support and bug fixing | 6 | 9 | 7.5 | Must-have | Joint test with SAP and UOB sandbox
P1L | PM/communication | 3 | 5 | 4 | Must-have | English-speaking PM/coordination
P1S | Lean Phase 1 MVP baseline | 45 | 75 | 60 | Baseline | Same scope as P1L
P1S | Stronger callback validation and idempotency | 4 | 5 | 4.5 | Recommended | Prevent duplicated callback updates
P1S | Exception handling for wrong amount/duplicate/unknown ref | 5 | 7 | 6 | Recommended | Reduce manual Finance AR work
P1S | SAP FI/AR posting or clearing enhancement | 8 | 12 | 10 | Optional | Depends on SAP FI/AR process
P1S | Operational monitoring and alerting | 3 | 5 | 4 | Optional | Support run operations
P1S | Additional regression/security testing | 5 | 6 | 5.5 | Recommended | Needed for production confidence
P2 | Field Power process analysis | 4 | 5 | 4.5 | Phase 2 | Confirm field/mobile flow
P2 | Mobile/field payment flow design | 4 | 5 | 4.5 | Phase 2 | Define user journey and states
P2 | Integration extension | 8 | 15 | 11.5 | Phase 2 | Reuse Phase 1 service where possible
P2 | SAP/Field Power mapping and update | 8 | 15 | 11.5 | Phase 2 | Map transactions back to SAP
P2 | Testing and rollout support | 6 | 10 | 8 | Phase 2 | UAT and deployment support

## Assumptions
Assumptions and Scope Control
Use these assumptions to keep Phase 1 small and protect margin.
No. | Assumption
1 | Phase 1 covers Counter Sales only.
2 | Currency is SGD.
3 | PayNow Corporate / UEN registration is handled by SCSKAP/customer.
4 | UOB provides API documentation, sandbox, credentials, certificate requirements, and webhook rules.
5 | SAP version and output technology are available for review.
6 | Existing invoice output exists and only needs QR/payment fields added.
7 | One payment reference maps to one SAP invoice.
8 | No partial payment, refund, chargeback, or multi-bank flow in Lean Phase 1.
9 | SAP production transport and approval process are handled by SCSKAP/customer.
Base Scope Exclusions
1 | Bank onboarding delays and production approval/certification outside normal implementation support.
2 | Refund, chargeback, multi-bank, multi-currency, or partial payment scenarios.
3 | Major SAP invoice form redesign beyond QR/payment data placement.
4 | Field Power Integration, dashboards, reporting portal, and advanced monitoring.
5 | SAP infrastructure changes, customer network/firewall changes, or production transport approval delays.

## Questions
Questions Before Final Quote
These must be answered before converting the MD range into a final fixed price.
Topic | Question | Priority | Owner/Status
SAP version | Which SAP version is used: ECC, S/4HANA On-Premise, S/4HANA Cloud, or SAP Business One? | High | Open
Output technology | Which invoice output technology is used: SAPscript, Smart Forms, Adobe Forms, or S/4HANA Output Management? | High | Open
PayNow registration | Does SCSKAP already have UOB PayNow Corporate registration and UEN suffix? | High | Open
UOB API access | Does UOB provide sandbox and API documentation for dynamic PayNow QR? | High | Open
Notification method | Is payment notification delivered by webhook/API, email, bank statement, or batch file? | High | Open
SAP update | Should SAP only mark payment status, or perform FI/AR clearing automatically? | High | Open
Exception scope | Are partial payment, overpayment, duplicate payment, and refund required in Phase 1? | Medium | Open
Rollout scope | Is Counter Sales one location/company code, or multiple? | Medium | Open
Volume | What is the expected transaction volume per day? | Medium | Open
Timeline | What is the target go-live date? | Medium | Open

## Commercial Notes
Commercial Notes
Suggested language and guardrails for proposal discussions.
Area | Guidance
Customer-facing answer | Yes, this system can be developed. We recommend a short technical discovery first, then a focused Phase 1 for Counter Sales: PayNow QR embedded into SAP Sales Invoice, amount/reference auto-populated, UOB payment notification routed back, and SAP transaction confirmation.
Budget strategy | Start small. Phase 0 gives customer a low-cost entry point and lets Rikkeisoft avoid unsafe assumptions.
Base offer | Lean Phase 1 MVP. Keep advanced exception handling, dashboards, Field Power, refunds, partial payments, and multi-bank support outside base scope.
Commercial model | Phase 0 fixed price. Phase 1 fixed scope or capped T&M. Phase 2 separate estimate after Phase 1.
Resource positioning | English-speaking PM/engineer is required. ABAP support should be included or reserved depending on SAP output technology.
Risk wording | QR code generation is straightforward; the main risks are UOB API access/security, bank callback validation, SAP output changes, and SAP FI/AR reconciliation.
Reference experience wording | If exact PayNow/UOB/SAP reference is not verified, say Rikkeisoft has similar enterprise integration experience and will confirm exact reference internally.
Do not include | Do not include bank onboarding delays, major SAP redesign, full auto-clearing, Field Power, or advanced monitoring in the lowest-cost base quote.
Presale next action | Propose Phase 0 discovery with SCSKAP and UOB/SAP stakeholders.

## References
References
Public source links used to ground the terminology and integration assumptions.
Source | Relevance | URL
ABS PayNow | PayNow Corporate supports entities receiving SGD through UEN and QR payments. | https://www.abs.org.sg/e-payments/pay-now
UOB PayNow Corporate | UOB supports PayNow Corporate and SGQR collection via UEN/QR. | https://www.uobgroup.com.sg/business/transact/payments/paynow-corporate.page
UOB API Services | UOB API services include FAST/PayNow services and Credit/Debit Notification API. | https://www.uobgroup.com/business/digital/uob-api-services.page
SAP Invoice Forms | SAP invoice forms/output can be configured for billing document printing/PDF output. | https://help.sap.com/docs/SAP_S4HANA_CLOUD/ddd685ebd8614e7b8d8eaf4d001e7c40/7ea0b78d5d8e48b5a5078f618ce2a747.html

## Noted
Phase 1 Counter Sales:
1 | Customer comes to counter.
2 | Staff creates SAP Sales Invoice.
3 | Invoice has PayNow QR.
4 | Customer scans and pays at counter.
5 | UOB sends payment notification.
6 | SAP is updated.
Phase 2 Field Power/mobile/field sales:
1 | Salesperson or technician visits customer site. | Why It Is More Complex Than Counter Sales
2 | They use a mobile/tablet app. | Field/mobile flow usually adds more work because:
3 | They create invoice/payment request from the field.
4 | App shows or generates PayNow QR. | Mobile app may need online/offline support.
5 | Customer scans and pays on-site. | User may be outside company network.
6 | UOB sends payment notification. | Payment status must sync between mobile app, SAP, and bank.
7 | SAP and the mobile/field system both show payment completed. | QR may need to be shown on mobile instead of printed invoice.
Need handle failed sync, duplicate payment, wrong amount, lost connection.
Field users may need receipt/payment confirmation immediately.
Chiến lược nên dùng
Vì khách nói budget thấp, không nên báo giá full scope ngay. Cách tiếp cận tốt nhất là chia thành:
Phase 0 - Paid discovery/design nhỏ
Mục tiêu: xác nhận SAP version, invoice output, UOB API, webhook, QR format, reconciliation rule.
Effort: 5-8 MD
Phase 1 - Lean MVP cho Counter Sales
Chỉ làm phần tạo QR trên SAP invoice, scan PayNow, nhận notification từ UOB/SG Bank, match invoice reference, cập nhật/confirm SAP.
Effort: 45-75 MD
Phase 2 - Field Power Integration
Để sau, không đưa vào base price.
Effort: 30-50 MD